## Sheet1
| Start Date | Completed | Remaining
Set Up Repo and Android Project | 2014-01-06 | 2 | 0
Project Plan | 2014-01-12 | 6 | 0
DB Schema Analysis | 2014-01-19 | 10 | 0
UML Diagram | 2014-02-08 | 9 | 0
Gantt Chart | 2014-02-16 | 2 | 0
Mongo Login/Signup Routes | 2014-02-20 | 0 | 5
Android Activity Layouts | 2014-02-25 | 0 | 10
Mongo Routes | 2014-03-07 | 0 | 14
Connect Mongo to Android/Website | 2014-03-21 | 0 | 14
Debugging and Testing | 2014-04-04 | 0 | 14
Final Report/Presentation | 2014-04-18 | 0 | 12